## Gantt Chart
GANTT CHART
PROJECT TITLE |  | JobLink - A job-board website |  |  |  |  | COMPANY NAME | [6 empty] | JobLink
PROJECT MANAGER |  | Fahim,Sadia,Jui,Rayhan |  |  |  |  | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | T | F | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirement
1.1 | Project Charter | Fahim,Sadia,Jui,Rayhan | 2024-08-15 | 2024-08-15 | 0 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Fahim,Sadia,Jui,Rayhan | 2024-08-22 | 2024-08-22 | 0 | 98% | bar: WEEK 2 T to WEEK 2 W
1.2 | Research | Fahim,Rayhan | 2024-08-24 | 2024-08-24 | 0 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Client Metting | Sadia,Jui | 2024-08-29 | 2024-08-30 | 1 | 40% | bar: WEEK 3 T
1.4 | Stakeholders | Public | 2024-08-29 | 2024-08-29 | 0 | 70% | bar: WEEK 3 F
2 | Analysis
2.1 | Scope and Goal Setting |  | 2024-09-01 | 2024-09-01 | 4 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget |  | 2024-09-01 | 2024-09-01 | 3 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Selctecing Program |  | 2024-09-01 | 2024-09-01 | 0 | 90% | bar: WEEK 5 T
3 | Modeling
3.1 | ER Diagram |  | 2024-09-15 | 2024-09-21 | 0 | 100% | bar: WEEK 5 W to WEEK 5 R
3.2 | Use Case Diagram |  | 2024-09-22 | 2024-09-28 | 0 | 98% | bar: WEEK 5 F to WEEK 6 T
3.3 | Dataflow Diagram |  | 2024-09-29 | 2024-10-06 | 0 | 90% | bar: WEEK 6 W
3.4 | Sate Diagram |  | 2024-10-13 | 2024-10-13 | 0 | 40% | bar: WEEK 6 R
3.5 | DFD0 & DFD 1 |  | 2024-10-14 | 2024-10-28 | 0 | 70% | bar: WEEK 6 R to WEEK 6 F
3.6 | Sequence Diagram |  | 2024-11-01 | 2024-10-11 | 0 | 35% | bar: WEEK 7 M
3.7 | Class Diagram |  | 2024-11-22 | 2024-11-28 | 0 | 20% | bar: WEEK 7 T to WEEK 7 W
4 | Development
4.1 | Programing |  | 2024-11-29 | 2024-11-10 | 0 | 90% | bar: WEEK 7 W to WEEK 7 F
4.2 | Implementation |  | 2024-11-10 | 2024-11-29 | 0 | 40% | bar: WEEK 7 F to WEEK 8 M
4.3 | Frontend Developing |  | 2024-10-23 | 2024-11-08 | 0 | 70% | bar: WEEK 8 M to WEEK 8 R
4.4 | Backend Finishing |  | 2024-11-01 | 2024-11-23 | 0 | 35% | bar: WEEK 8 W to WEEK 9 F
5 | Testing
4.1 | Unit Testing |  | 2024-10-23 | 2024-12-01 | 0 | 90% | bar: WEEK 10 M to WEEK 10 W
4.2 | Database Testing |  | 2024-11-29 | 2024-11-29 | 0 | 40% | bar: WEEK 10 W to WEEK 11 M
4.3 | Effort and Cost Tracking |  | 2024-12-06 | 2024-12-08 | 0 | 70% | bar: WEEK 11 M to WEEK 12 W
4.4 | Project Performance |  | 2024-12-06 | 2024-12-08 | 0 | 35% | bar: WEEK 12 W to WEEK 12 R
4.5 | gtmetrix.com |  | 2024-12-06 | 2024-12-08 | 0 | 25% | bar: WEEK 12 F